## 📊 Summary
Tower Defence — Updated To-Do (Trello + Code Analysis)
Synced with Trello: Arternix Intern + Code: E:\project\Intern-AX ¦ 22 May 2025
✅ Done in Code |  | 🔄 Doing |  | 📋 To Do | ⚠️ Trello Updated
21 |  | 10 |  | 14 | 18
🔄 Trello Updates Performed This Session
Action | Card Name | Change | Source
ย้าย → Done | World Map Scene | To Do → Done | Maps.scene found in code
ย้าย → Done | World Map Scene Script | To Do → Done | WorldMapManager.ts found in code
สร้าง Done card | Enemy Pathfinding System | New → Done | EnemyMovement.ts + WayPoint.ts
สร้าง Done card | Wave Spawn System | New → Done | WaveManager.ts
สร้าง Done card | Tower Placement & Drag | New → Done | PlacementSlot.ts + TowerDrageHandler.ts
สร้าง Done card | Tower Base System | New → Done | TowerBase + Controller + Manager
สร้าง Done card | Bullet System | New → Done | bullet.ts + SplashArea.ts + Prefabs
สร้าง Done card | Stage Config & Data System | New → Done | StageConfig + StageDataManager + StageNode
สร้าง Done card | HUD: Gold + Wave + Notification | New → Done | GoldUI + WaveUI + NotificationUI
สร้าง Done card | Core Systems | New → Done | BaseManager + ResourceManager + GameConfig + BuffType
สร้าง Done card | Stage 1 Tilemap (RV1.tmx) | New → Done | RV1.tmx + Tilemap_color1-5.png
สร้าง To Do card | Damage Type System | New → To Do | ยังไม่มีในโค้ด
สร้าง To Do card | Player HP & Leak Damage | New → To Do | ยังไม่มีในโค้ด
สร้าง To Do card | Tower Upgrade System (T1→T2) | New → To Do | ยังไม่มีในโค้ด
สร้าง To Do card | Enemy Sprites (folder empty!) | New → To Do | GameAssets/Enemies/ ว่าง
สร้าง To Do card | Boss: Plague Knight | New → To Do | ยังไม่มีในโค้ด
สร้าง To Do card | Stage 2: Haunted Graveyard | New → To Do | ยังไม่มีในโค้ด
สร้าง To Do card | Stage 3: Fallen Castle | New → To Do | ยังไม่มีในโค้ด
สร้าง To Do card | BGM + Boss Sprites | New → To Do | Audio folder ว่าง
สร้าง To Do card | QA: Test Plans | New → To Do | ยังไม่มีในโค้ด

## 📋 Updated Task List
Full Updated Task List — Based on Code Analysis
# | Task / Feature | Assignee | Source / Files | Status | Category | Notes
✅ DONE — พบในโค้ดแล้ว
D-01 | Create Main Menu Scene | FE1 | main_menu.scene | ✅ Done | Scene/UI
D-02 | Create Login Scene + Script | FE1 | login.scene / Login.ts | ✅ Done | Scene/UI
D-03 | Create Register Scene + Script | FE1 | register.scene / Register.ts | ✅ Done | Scene/UI
D-04 | Create Landing Page Scene + Script | FE1 | landing_page.scene / LandingPage.ts | ✅ Done | Scene/UI | เหลือ Guest Scene เชื่อม
D-05 | Setting UI (Scene) | FE1 | (scene exists) | ✅ Done | Scene/UI | Script ยัง To Do
D-06 | World Map Scene + Script | FE2 | Maps.scene / WorldMapManager.ts | ✅ Done | Scene/UI | ย้ายจาก To Do แล้ว
D-07 | Enemy Pathfinding System | FE2 | EnemyMovement.ts + WayPoint.ts + PathManager.ts | ✅ Done | Gameplay | Waypoint-based ครบ
D-08 | Wave Spawn System | FE2 | WaveManager.ts | ✅ Done | Gameplay
D-09 | Tower Placement & Drag System | FE2 | PlacementSlot.ts + TowerDrageHandler.ts | ✅ Done | Gameplay
D-10 | Tower Base System | FE1 | TowerBase + Controller + Manager + detection_area | ✅ Done | Tower
D-11 | Bullet System (Normal + Splash) | FE1 | bullet.ts + SplashArea.ts + Prefabs | ✅ Done | Tower
D-12 | Stage Config & Data System | FE2 | StageConfig + StageDataManager + StageNode | ✅ Done | Stage
D-13 | HUD: Gold + Wave + Notification UI | FE1 | GoldUI.ts + WaveUI.ts + NotificationUI.ts | ✅ Done | Scene/UI
D-14 | Core Systems (Manager, Config, Buff) | FE1 | BaseManager + ResourceManager + GameConfig + BuffType | ✅ Done | Gameplay
D-15 | Archer Tower (Sprite + Anim + Prefab) | AM | Archer.prefab + A-Idle/Attack.png + .anim | ✅ Done | Asset | Animation ครบ
D-16 | Bomber Tower (Sprite + Prefab) | AM | Bomber.prefab + B-Idle/Attack.png | ✅ Done | Asset
D-17 | Gold Mine Tower (Sprite + Prefab) | AM | GoldMine.prefab + Goldmine1-3.png | ✅ Done | Asset
D-18 | Zombie + Bandit Prefabs | FE2 | Zombie.prefab + Bandit.prefab | ✅ Done | Enemy | Sprite ยังไม่มี!
D-19 | Stage 1 Tilemap (Ruined Village) | AM | RV1.tmx + Tilemap_color1-5.png | ✅ Done | Asset
D-20 | UI Assets (Buttons, Panels, WorldMap) | AM | Button/ + Panel/ + WorldMap.png + Stage1.png | ✅ Done | Asset
D-21 | Homebase Assets | AM | Barracks/Castle/House1/Monastery.png | ✅ Done | Asset
🔄 DOING — กำลังทำอยู่
W-01 | Implement Login Scene Script | FE1 | Login.ts (in progress) | 🔄 Doing | Script
W-02 | Implement Register Scene Script | FE1 | Register.ts (in progress) | 🔄 Doing | Script
W-03 | Implement Landing Page Script | FE1 | LandingPage.ts | 🔄 Doing | Script | เหลือ Guest Scene
W-04 | Gameplay Scene + Core Loop | FE2 | scene.scene + Gameplay Script | 🔄 Doing | Gameplay
W-05 | Attack/Support Tower Interface | FE1 | Test/AttackTower.ts + ITower.ts + SupportTower.ts | 🔄 Doing | Tower | อยู่ใน Test folder
W-06 | Priest Tower Logic (Buff) | FE2 | BuffType.ts มีแล้ว — logic pending | 🔄 Doing | Tower
W-07 | Enemy Sprite + Animation | AM | GameAssets/Enemies/ (empty — in progress) | 🔄 Doing | Asset | Folder ว่าง!
W-08 | Game SFX | AM | (in progress) | 🔄 Doing | Asset
📋 TO DO — ยังไม่มีในโค้ด
T-01 | Setting UI Script | FE1 | - | 📋 To Do | Script
T-02 | Implement Main Menu Script | FE1 | - | 📋 To Do | Script
T-03 | Stage (Collection) Scene + Script | FE2 | - | 📋 To Do | Scene/UI
T-04 | Stage (Loadout) Scene + Script | FE1 | - | 📋 To Do | Scene/UI | Slot limit: 4/5
T-05 | Result Screen (Guest & Login) | FE1 | - | 📋 To Do | Scene/UI
T-06 | Damage Type System (Phys/Magic/Holy) | FE1 | - | 📋 To Do | Gameplay | Critical!
T-07 | Player HP & Leak Damage System | FE2 | - | 📋 To Do | Gameplay | HP=20, leak dmg
T-08 | Gold Economy (Kill + Wave clear) | FE1 | - | 📋 To Do | Economy
T-09 | Tower Upgrade System (T1 → T2) | FE1 | - | 📋 To Do | Tower | 7 towers
T-10 | Enemy Sprites (folder EMPTY!) | AM | GameAssets/Enemies/ — ว่าง | 📋 To Do | Asset | urgent!
T-11 | Boss: Plague Knight (Poison Aura) | FE2 | - | 📋 To Do | Boss
T-12 | Stage 2: Haunted Graveyard | FE2 | - | 📋 To Do | Stage | Lich, Necro, Skeleton
T-13 | Stage 3: Fallen Castle | FE2 | - | 📋 To Do | Stage | Dark Knight, Orc, Soldier
T-14 | BGM + Boss Sprites (3 stages) | AM | Audio/ ว่าง | 📋 To Do | Asset
T-15 | QA: Test Plans (all stages) | QA | - | 📋 To Do | QA

## 🗂️ Kanban
Kanban Board — Updated from Code
✅ Done (21) | 🔄 Doing (8) | 📋 To Do (15)
Main Menu / Login / Register / Landing Scenes | Login / Register / Landing Page Scripts | Setting UI Script + Main Menu Script
World Map Scene + Script ← moved from To Do | Gameplay Scene + Core Loop | Stage Collection + Loadout Scenes
Enemy Pathfinding (EnemyMovement.ts) | Attack/Support Tower Interface (Test/) | Result Screen
Wave Spawn System (WaveManager.ts) | Priest Tower Logic (BuffType.ts) | Damage Type System 🔴 Critical
Tower Placement & Drag System | Enemy Sprites ⚠️ folder ว่าง! | Player HP & Leak Damage 🔴 Critical
Tower Base + Controller + Manager | Game SFX | Gold Economy System
Bullet System (Normal + Splash) | Tower Animation (partial) | Tower Upgrade System (T1→T2)
Stage Config & Data System | Enemy Animation (partial) | Enemy Sprites 🔴 Urgent (folder empty)
HUD: Gold + Wave + Notification |  | Boss: Plague Knight (Poison Aura)
Core Systems (Manager, Config, Buff) |  | Stage 2: Haunted Graveyard
Archer Tower (Sprite + Anim + Prefab) |  | Stage 3: Fallen Castle
Bomber + Gold Mine Tower (Sprites) |  | BGM + Boss Sprites (Audio folder ว่าง)
Stage 1 Tilemap — RV1.tmx |  | QA: Test Plans
UI Assets + Homebase Assets |  | Gladiator Tower
Zombie + Bandit Prefabs |  | Wizard / Cannoneer / Catapulter
⚠️ Items สีส้มแดง = urgent / critical — ต้องแก้ก่อน